        ASSIGNMENT6.1

1.How do you evaluate the performance of a project in agile?
     The evaluation is based on outcomes rather than outputs,where customer satisfication is given higher priority and even some out of scope things are added if customer demands(if it is feasible).Key points considered are,
- Velocity :The measure of how many user stories can be delivered within the sprint.These are basically the story points.They can be baseline velocity(expected) or actual velocity(reality).
- Hit rate:These are the success rate,which tells about percentage work completed over given baseline.
- Work Remaining On Task:These tells about how much person days are reamining based on amount of work completed.The work remaining may go down if remaining story points are not complicated or it may increase if the task is more complicated than assumed.
- Project Cost:Is amount of cost spent on a project,amount is estimated based on CPI,SPI,EBV.
  Here ,CPI compares baseline cost and actual cost for a story point.If CPI=1 is ideal one,CPI>1 spending is less, CPI<1 spending is less than expected.
  SPI,compares the actual velocity over baseline velocity.
        SPI>1 completed before schedule ,SPI<1 delayed.

EBV :it is subjective where it emphasis on value which is earned after the release.
Thus performance is purely based on above mentioned factors ,In agile as the requirements will be changing based on demand and hence it more subjective than objective.

2.Compare traditional monitoring & control with agile monitoring & control with respect to metrics generation

Traditional monitoring & control	Agile monitoring & control
Expected and reality must be same,as in most of cases there is no addtion of things are entertained.	As agile is more flexible expected and reality may change based on change in requirements.
In CPI,baseline and actual cost / per story must match.	In CPI,actual cost may change per story point depending on the complexity.
Here,business value consists of all story points.	Here,business value does not consists of all story points(training is not included).
It does not emphasis on EBV,the success measurment purely depends on outputs.	It emphasis on EBV,the success measured is based on the outcomes.
Sprint no ,Pcn,TPC,AV,Acn,TAC and others metrics are pre-determined,any change is considered as bad practise unless approved by mangement.	Sprint no,PCn,TPC,AV,Acn,TAC and others metrics are may change and always conflicts and changes are welcome

3.With a total project budget of $ 175,000, and having
completed one out of four Iterations, we have this product backlog and these actuals:
Feature	Estimate / (storypoints)	Completed / (storypoints)	Actual Cost(1000s / dollars)
Welcome Screen	10	10	15
Advert - Splash Screen	20	20	30
Login Screen	10	10	20
Personalized Google Ads	20
Catalog Browser	20
Catalog Editor	10
Shopping Basket Browser	5
Shopping Card Editor	25
Check-out Process	20
Invoice Calculation	10
Credit Card Verification	10
PayPal Payment Handling	20
Order Confirmation Email	20
Totals	200	40	65

In our example,after on iteration we should be at 25% complete
 calculate planned value,actual % complete,earned value

Planned value=The percent of expected complete multiplied by total budget=25% of $17500=$4375
Actual % complete=total no of story points completed to total no of storypoints planned=40/200=20% complete
Earned value=Total budget multiplied with actual percent complete=20% of $175,000=$35,000

